## Project Plan Dec 4
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | In progress |  | 2022-10-25 | 2022-11-15
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet | complete |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump | completed |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example | completed |  | 2022-10-24 | 2022-11-13
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms 1-2 designs with implementations | Portfolio of design ideas | all members | completed |  | 2022-11-08 | 2022-11-20
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members | completed |  | 2022-11-13 | 2022-11-13
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members | completed |  | 2022-11-20 | 2022-11-20
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present ideas to sponsor for feedback | Sponsor's feedback on our main ideas | All members, sponsor |  |  |  | 2022-12-09
5.5 |  | Complete Decision Matrix | 5.1-5.4 | complete decision matrix | Decision matrix submitted to educsourced |  | in progress |  | 2022-11-20 | 2022-12-04
5.6 |  | Decide on main design idea as a team | 5.1-5.5 | Discuss decision matrix and decide on a main idea | Final idea chosen | all members | in progress |  | 2022-11-27 | 2022-12-04
5.7 |  | Hold conceptual design review | 5.1-5.6 | Hold conceptual design review | hold conceptual design review and get sponsor feedback | all members and sponsor |  |  | 2022-11-20 | 2023-01-22
5.8 |  | Submit team contract for winter break into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | in progress |  | 2022-11-20 | 2022-12-05
5.9 |  | Finish project plan through end of spring semester | n/A | submit project plan to canvas | Submit to canvas in next couple of weeks | internet, canvas | complete |  | 2022-11-20 | 2022-12-09
5.1 |  | Everyone fill out decision matrix rankings so we can average scores | 5.1-5.8 | Finalize decision matrix for CDR | Submit DM to Edusourced | internet, Teams | in progress |  | 2022-11-27 | 2022-12-09
5.11 |  | Complete Conceptual design Report | 5.1-5.10 | Decide on conceptual designs to present to sponsor with a suggestion for the best design | Completed Conceptual Design REPORT | all members, Teams | in progress |  |  | 2023-01-21
5.12 |  | Hold conceptual design review | 5.11 | Hold conceptual design review to present conceptual design report to sponsor and decide on a single design to pursue | The single design to be pursued will be chosen and signed off by the sponsor | all members and sponsor |  |  |  | 2023-01-21
5.13 |  | Bring spring schedule to weekly meeting | n/a | bring spring schedule to weekly meetings | plan new spring meeting time with sponsor | all members and sponsor | in progress |  | 12.4.2022 | 2022-12-05
5.14 |  | Edit eng spec report | 4.11 | edit and submit eng spec report to canvas | eng spec report is submitted to canvas | all/whoever has time | in progress |  | 2022-12-04 | 2022-12-09
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5, 12.3 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5, 12.3 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5, 12.3 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5, 12.3 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12 | Handbook Requirements
12.1 |  | Test Plan | 7.5,8.5,9.5,10.5 | create a detailed testing plan to test protoype as per canvas guidelines | finished test plan | all members, teams |  |  | 2023-02-17 | 2023-02-24
12.2 |  | Present Test Plan to Advisor | 12.1 | Present test plan to advisor for approval to begin testing protoype and to write the test plan REPORT | approval to begin testing | all members, advisor meeting |  |  | 2023-02-27 | 2023-02-27
12.3 |  | Write Test Plan REPORT for Final report | 12.2 | test plan report written according to canvas guidelines | finalized test plan REPORT for final report | all members, teams |  |  | 2023-02-27 | 2023-03-03
12.4 |  | Prototype testing | 12.3 | test the prototype | tested protoype | completed prototypes, all members |  |  | 2023-02-27 | 2023-03-17
12.5 |  | Testing Report | 12.4 | perform analysis on the tests done and write the Testing report as per canvas guidelines | finalized test REPORT for final report | all members, teams |  |  | 2023-03-17 | 2023-03-31
13 | Critical Design Review
13.1 |  | Critical design documents |  | have the four critical design documents that are to be presented during the critical design review completed | critical design documents |  |  |  |  | 2023-03-31
13.2 |  | Critical design review |  | present the critical design documents to the sponsor to receive approval for final design completion | signed critical design review document by the sponsor to finish the design
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4 |  | Engineering design exposition powerpoint presentation | all of the above | create an extremely brief PP presentation introducing the project | powerpoint presentation | most likely designated |  |  |  | 2023-05-02
|  | Engineering design exposition poster presentation | all of the above | create a professional quality poster to show the design created by the team at the engineering design exposition | poster presentation | All team members |  |  |  | 2023-05-02

## Project Plan Nov 27
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | In progress |  | 2022-10-25 | 2022-11-15
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet | complete |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump | completed |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example | completed |  | 2022-10-24 | 2022-11-13
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms 1-2 designs with implementations | Portfolio of design ideas | all members | completed |  | 2022-11-08 | 2022-11-20
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members | completed |  | 2022-11-13 | 2022-11-13
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members | completed |  | 2022-11-20 | 2022-11-20
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present ideas to sponsor for feedback | Sponsor's feedback on our main ideas | All members, sponsor |  |  |  | 2022-12-09
5.5 |  | Complete Decision Matrix | 5.1-5.4 | complete decision matrix | Decision matrix submitted to educsourced |  | in progress |  | 2022-11-20 | 2022-12-04
5.6 |  | Decide on main design idea as a team | 5.1-5.5 | Discuss decision matrix and decide on a main idea | Final idea chosen | all members |  |  | 2022-11-27 | 2022-12-04
5.7 |  | Hold conceptual design review | 5.1-5.6 | Hold conceptual design review | hold conceptual design review and get sponsor feedback | all members and sponsor |  |  | 2022-11-20 | 2022-12-09
5.8 |  | Submit team contract for winter break into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | in progress |  | 2022-11-20 | 2022-12-01
5.9 |  | Finish project plan through end of spring semester | n/A | submit project plan to canvas | Submit to canvas in next couple of weeks | internet, canvas |  |  | 2022-11-20 | 2022-12-09
5.1 |  | Everyone fill out decision matrix rankings so we can average scores | 5.1-5.8 | Finalize decision matrix for CDR | Submit DM to Edusourced | internet, Teams | in progress |  | 2022-11-27 | 2022-12-09
5.11 |  | Complete Conceptual design Report | 5.1-5.10 | Decide on conceptual designs to present to sponsor with a suggestion for the best design | Completed Conceptual Design REPORT | all members, Teams | in progress |  |  | 2023-01-21
5.12 |  | Hold conceptual design review | 5.11 | Hold conceptual design review to present conceptual design report to sponsor and decide on a single design to pursue | The single design to be pursued will be chosen and signed off by the sponsor | all members and sponsor |  |  |  | 2023-01-21
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1 |  | Test Plan | 7.5,8.5,9.5,10.5 | create a detailed testing plan to test protoype as per canvas guidelines | finished test plan | all members, teams |  |  | 2023-02-17 | 2023-02-24
12.2 |  | Present Test Plan to Advisor | 12.1 | Present test plan to advisor for approval to begin testing protoype and to write the test plan REPORT | approval to begin testing | all members, advisor meeting |  |  | 2023-02-27 | 2023-02-27
12.3 |  | Write Test Plan REPORT for Final report | 12.2 | test plan report written according to canvas guidelines | finalized test plan REPORT for final report | all members, teams |  |  | 2023-02-27 | 2023-03-03
12.4 |  | Prototype testing | 12.3 | test the prototype | tested protoype | completed prototypes, all members |  |  | 2023-02-27 | 2023-03-17
12.5 |  | Testing Report | 12.4 | perform analysis on the tests done and write the Testing report as per canvas guidelines | finalized test REPORT for final report | all members, teams |  |  | 2023-03-17 | 2023-03-31
13
13.1 |  | Critical design documents |  | have the four critical design documents that are to be presented during the critical design review completed | critical design documents |  |  |  |  | 2023-03-31
13.2 |  | Critical design review |  | present the critical design documents to the sponsor to receive approval for final design completion | signed critical design review document by the sponsor to finish the design
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4 |  | Engineering design exposition powerpoint presentation | all of the above | create an extremely brief PP presentation introducing the project | powerpoint presentation | most likely designated |  |  |  | 2023-05-02
|  | Engineering design exposition poster presentation | all of the above | create a professional quality poster to show the design created by the team at the engineering design exposition | poster presentation | All team members |  |  |  | 2023-05-02

## Project Plan Nov 20
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | In progress |  | 2022-10-25 | 2022-11-15
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet | complete |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump | completed |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example | completed |  | 2022-10-24 | 2022-11-13
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms 1-2 designs with implementations | Portfolio of design ideas | all members | completed |  | 2022-11-08 | 2022-11-20
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members | completed |  | 2022-11-13 | 2022-11-13
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members | completed |  | 2022-11-20 | 2022-11-20
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present ideas to sponsor for feedback | Sponsor's feedback on our main ideas | All members, sponsor |  |  |  | 2022-12-09
5.5 |  | Complete Decision Matrix | 5.1-5.4 | complete decision matrix | Decision matrix submitted to educsourced |  | in progress |  | 2022-11-20 | 2022-12-09
5.6 |  | Decide on main design idea as a team | 5.1-5.5 | Discuss decision matrix and decide on a main idea | Final idea chosen | all members |  |  |  | 2022-12-02
5.7 |  | Hold conceptual design review | 5.1-5.6 | Hold conceptual design review | hold conceptual design review and get sponsor feedback | all members and sponsor |  |  | 2022-11-20 | 2022-12-09
5.8 |  | Submit team contract for winter break into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-11-20 | 2022-12-01
5.9 |  | Finish project plan through end of spring semester | n/A | submit project plan to canvas | Submit to canvas in next couple of weeks | internet, canvas |  |  | 2022-11-20 | 2022-12-09
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan Nov 13
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | In progress |  | 2022-10-25 | 2022-11-15
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet | complete |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump | completed |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example | in progress |  | 2022-10-24 | 2022-11-13
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms 1-2 designs with implementations | Portfolio of design ideas | all members | in progress |  | 2022-11-08 | 2022-11-13
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members | in progress |  | 2022-11-13 | 2022-11-13
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members |  |  | 2022-11-20
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan Nov 6
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | completed |  | 2022-10-25 | 2022-11-01
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet | complete |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump | completed |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example | in progress |  | 2022-10-24 | 2022-11-13
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms 1-2 designs with implementations | Portfolio of design ideas | all members | in progress |  | 2022-11-08 | 2022-11-13
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members |  |  | 2022-11-13 | 2022-11-13
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan Oct 30
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor | completed |  | 2022-10-25 | 2022-11-01
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor | completed |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document | completed |  | 2022-10-24 | 2022-11-01
4.9 |  | Complete engineering specification outline | 4.1-4.8 | Each member spend at least 1 hr on outline | Completed outline | internet |  |  | 2022-10-30 | 2022-11-08
4.1 |  | Take apart pressure regulator/pump | n/a | Take notes on things learned | meet as group and do this | Hayden's house, pressure regulator/pump |  |  | 2022-10-31 | 2022-10-31
4.11 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example |  |  | 2022-10-24 | 2022-11-15
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms at least 5 solutions | Portfolio of design ideas | all members |  |  | 2022-11-08 | 2022-11-22
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan Oct 24
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet | complete |  | 2022-10-11 | 2022-10-16
2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access | complete |  | 2022-10-10 | 2022-10-16
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper | ongoing |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet | ongoing |  | 2022-10-12 | 2022-10-22
4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs | ongoing |  | 2022-10-16 | 2022-10-23
4.5 |  | Create engineering specification document | 4.1-4.4 | Create engineering specification document | Show faculty completed eng specification document at 10/24 meeting |  | ready for 10/24 meeting |  | 2022-10-16 | 2022-10-24
4.6 |  | Share engineering specification document with sponsor | 4.5 | Share engineering specification document with sponsor | sponsor either signs off on it or we receive feedback and edit document again before resubmitting | Sponsor |  |  | 2022-10-25 | 2022-11-01
4.7 |  | Complete House of Quality | 4.1-4.6 | Complete house of quality | Submit house off quality to canvas on Friday | canvas, house of quality template, canvas lectures, sponsor |  |  | 2022-10-24 | 2022-10-28
4.8 |  | Meet with sponsor to show him engineering specification document and house of quality | 4.5-4.7 | Schedule meeting with sponsor to show him engineering specification document and house of quality | Meet with sponsor to discuss engineering specificaiton document and house of quality | team, sponsor, eng spec document and house of quality document |  |  | 2022-10-24 | 2022-11-01
4.9 |  | Write engineering specification report | 4.1-4.8 | Write engineering specification report | Submit to canvas in next couple of weeks | canvas template/example |  |  | 2022-10-24 | 2022-11-10
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms at least 5 solutions | Portfolio of design ideas | all members
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan oct 8
|  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
1 | Create Project Plan
1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
2 | Create Team Contract
2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
3 | Visit / volunteer at facility
3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
4 | Conduct research about subject
4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper |  |  | 2022-10-06 | 2022-10-21
4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet |  |  | 2022-10-12 | 2022-10-22
4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet |  |  | 2022-10-12 | 2022-10-22
5 | Choosing a Design Direction
5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms at least 5 solutions | Portfolio of design ideas | all members
5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members
5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members
5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
6 | Develop Method to Load Empty Pouches
6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
7 | Develop Method to Open Pouches with Gaseous Nitrogen
7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
8 | Develop Method to Fill Pouch with Wine
8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
9 | Develop Method to Seal Pouches with Cap
9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
10 | Develop Method to Offload Filled Pouch
10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
11 | Contected Functionality
11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
14 | Turn in final requirements
14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Project Plan oct 16
|  |  |  | what is needed before hand inorder to do the task (can be other task numbers) | More detailed explaination of task | Defined output of a what is expected (should NOT be another task) | Any resourses you might need to accomplish the task |  | Solutions to possible problems or altrnatives
| Task # | Tasks | Subtask | Input | Task Action | Output | Resource :3 | Progress | Solutions | Start date | End date
| 1 | Create Project Plan
| 1.1 |  | Each member spend 30 mins adding/editing this document | Project Plan Template | Fill out initial project plan to best extent using what we currently know | Completion and submission of this excel sheet | internet access, sllides on canvas about what a project plan should contain and the example of a project plan | complete |  | 2022-10-03 | ongoing
| 1.2 |  | Each member reviews final document once everyone has contributed | each member needs to have spent 30 mins adding to this document before reviewing it as a team | Discuss the tasks and decide if anything Is missing or needs to be added or subtracted | Final project plan is complete | All team members | complete |  | 2022-10-03 | ongoing
| 1.3 |  | Submit project plan via canvas | The final draft of our intiial project plan | Submit initial project plan on canvas | Assignment is completed in canvas | internet access | complete |  | 2022-10-03 | 2022-10-07
| 1.4 |  | Edit Project plan as needed to ensure consistency throughout format and add detail | Project plan | Edit project plan | updated version of project plan | internet access |  |  | 2022-10-07 | ongoing
| 1.5 |  | Fill out and Submit weekly update on canvas | Updated project plan | Fill out and submit weekly update on canvas | Submitted weekly update | internet access, weekly update template | complete |  | 2022-10-09 | ongoing (weekly)
| 1.6 |  | Submit MAE engineering notebook PDF or bring to class | Information gained throughout week | Fill out engineering notebook with information learned from week | submitted weekly engineering notebook | internet, Grace's notebook | complete |  | 2022-10-09 | ongoing
| 1.7 |  | Edit project plan with plan for modelling product online | none | edit project plan adding plan for online modelling | edited project plan | internet | complete |  | 2022-10-11 | 2022-10-16
| 1.8 |  | Create schedule for which team member updates project plan and which compeltes weekly summary | N/A | Create schedule | More organization and responsibility diffusion | internet, team schedule document in team files |  |  | 2022-10-11 | 2022-10-16
| 2 | Create Team Contract
| 2.1 |  | Look at sample contract | computer | spend time online looking at other contracts that have been written for smaller projects | mind ready for brainstorming ideas | internet access, computer, writing utensil, and paper | complete |  | 2022-10-03 | 2022-10-06
| 2.2 |  | Brainstorm main ideas |  | spend a little bit of time thinking of ideas and writing them down | ideas ready to be used to complete team contract | writing utensile and paper | complete |  | 2022-10-03 | 10/7/2022 at 11:59
| 2.3 |  | Compile ideas into final contract | contract template | use written ideas to add to current file of contract in teams document. Leave document in a state that can be turned in. | Contract ready to be submitted onto convas | internet access, computer, ideas | complete |  | 2022-10-03 | 10/7/2022 at 11:59
| 2.4 |  | Submit team contract into canvas | The final draft of our intiial project plan | Submit team contract on canvas | Assignment is completed in canvas | internet access, computer | complete |  | 2022-10-03 | 10/7/2022 at 11:59
| 2.5 |  | Edit team contract section about disagreements to say that we talk to faculty advisors before consulting sponsor about disagreements | 2.1-2.4 | edit team contract | resubmit team contract | internet |  |  | 2022-10-11 | 2022-10-16
| 2.6 |  | Create problem statement and add to team contract | 1,2.1-2.4,3 | create problem statement and share with sponsor | Udpated team contract | internet access |  |  | 2022-10-10 | 2022-10-16
| 3 | Visit / volunteer at facility
| 3.1 |  | Brainstorm questions to ask beforehand |  | brainstorm questions to ask client. make sure to obtain values crucial to functionality of end product. | questions to ask client | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
| 3.3 |  | Take as many notes as possible |  | take as many notes as possible on characteristics of the pouching process that are pertinent to automation | pouch filling characteristic notes | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
| 3.4 |  | Visit Evergood facility and ask sponsor questions | team schedule/ availability Questions for sponsor f/ team | If time is alloted, use this time at the facility to sit down with the sponsor to ask some initial questions about meetings and general expectations between the team and the sponsor | insight on sponsors expectations and availability for meetings. | writing utensile and paper/computer | complete |  | 2022-10-06 | 2022-10-17
| 4 | Conduct research about subject
| 4.1 |  | superficial packaging automation research | 3.4 | watch videos on different methods of packaging automation including boxing, canning, kaprisun pouching, etc. Write down nuances. | nuances to use for brainstorming | internet access, computer and or pen and paper |  |  | 2022-10-06 | 2022-10-21
| 4.2 |  | Conduct Market research on existing solutions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet |  |  | 2022-10-12
| 4.3 |  | Research other applicable mechanisms and their functions | 3.4 | each member researches for at least 1 hr | engineering notebook submission on research notes | internet |  |  | 2022-10-12 | 2022-10-22
| 4.4 |  | Review manufacturer's solution specifications that sponsor sends us |  | Review manufacturer's solution specifications that sponsor sends us | engineering notebook submission on research notes | email from sponsor including manufacturer's specs |  |  | 2022-10-16 | 2022-10-23
| 5 | Choosing a Design Direction
| 5.1 |  | Brainstorm possible solutions | all of 4, all of 3 | Each member brainstorms at least 5 solutions | Portfolio of design ideas | all members
| 5.2 |  | Discuss possible solutions and try to build on each others' ideas | 5.1 | Group discussion on ideas | Updated portfolio of design ideas | all members
| 5.3 |  | Go through process of elimination of ideas and narrow down to 3-5 ideas | 5.1 and 5.2 | Discuss the ideas and eliminate infeasible ones | Narrowed down portfolio of design ideas | all members
| 5.4 |  | Present 3-5 ideas to Sponsor for feedback | 5.3 | Present 3-5 ideas to sponsor for feedback | Sponsor's feedback on our 3-5 main ideas | All members, sponsor
| 5.5 |  | Decide on main design idea as a team | 5.4 | Discuss and decide on a main idea | Final idea chosen | all members
| 6 | Develop Method to Load Empty Pouches
Should Task 5 be creating a list of possible solutions that would include narrowing down our solution to the best 1 or 2 to present to our sponsor? Then 6 would be choosing a design and figuring out what materials we may need and stuff to then go through each phase of the automation process? Let me know idk | 6.1 |  | Develop a loading area for empty pouches | 4 | Some form of mass storage of pouches that can hold pouches within reach of the machine | Design to be used in assembly
| 6.2 |  | Develop a means of securing a single pouch from the loading area | 4 | Allow for the machine to grab one pouch from the loading area and hold the pouch in a way that it can be filled. | Design to be used in assembly
| 6.3 |  | Write control program for loading pouches | 6.1-2 |  | Code for microcontroller
| 6.4 |  | Purchase Loader Materials | 6.1-2 |  | Materials list (with budget)
| 6.5 |  | Assemble Loading Mechanism | 6.4 | Build pouch loading system for feeding empty pouches into the machine | Working Prototype
| 6.6 |  | Create solidworks design | 4,5, 6.1-6.5 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks
| 7 | Develop Method to Open Pouches with Gaseous Nitrogen
| 7.1 |  | prior research | 4 | research proven methods of delivering gaseas nitrogen to packaging | knownledge of conventional nitrogen package deliver | internet |  |  | 2022-10-21 | 2022-11-04
| 7.2 |  | Brain Storming | 4 | Brainstorm methods of delivering gaseas nitrogen to pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
| 7.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
| 7.4 |  | Team Review | 7.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
| 7.5 |  | Prototype1 | 7.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
| 7.6 |  | Test | 7.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
| 7.7 |  | Final Design | 7.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
| 7.8` |  | Create solidworks design | 4,5,6,7.1-7.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 3/17/2023` | 2023-04-14
| 8 | Develop Method to Fill Pouch with Wine
| 8.1 |  | prior research | 4 | research proven methods of delivering liquids to packaging | knowledge of convention liquid package delivery | internet |  |  | 2022-10-21 | 2022-11-04
| 8.2 |  | Brain Storming | 4 | brainstorm methods of delivering liquids to pouches that mesh with other methods of product being developed. | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
| 8.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
| 8.4 |  | Team Review | 8.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
| 8.5 |  | Prototype1 | 8.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
| 8.6 |  | Test | 8.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
| 8.7 |  | Final Design | 8.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
| 8.8 |  | Create solidworks design | 4,5,6,7,8.1-8.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
| 9 | Develop Method to Seal Pouches with Cap
| 9.1 |  | prior research | 4 | research proven methods of sealing packages | knowledge of conventional liquid package sealing | internet |  |  | 2022-10-21 | 2022-11-04
| 9.2 |  | Brain Storming | 4 | braintstorm methods of sealing pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
| 9.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
| 9.4 |  | Team Review | 9.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
| 9.5 |  | Prototype1 | 9.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
| 9.6 |  | Test | 9.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
| 9.7 |  | Final Design | 9.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
| 9.8 |  | Create solidworks design | 4,5,6,7,8,9.1-9.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
| 10 | Develop Method to Offload Filled Pouch
| 10.1 |  | prior research | 4 | reserach proven methods of offloading packages | knowledge of conventional package offload. | internet |  |  | 2022-10-21 | 2022-11-04
| 10.2 |  | Brain Storming | 4 | brainstorm methods of offloading pouches that mesh with other methods of product being developed | Ideas for a design | copmuter/pen and paper |  |  | 2022-11-04 | 2022-11-18
| 10.3 |  | Design | 4 | Complete a cad file of design for machining | Preliminary design | solidoworks/autocad |  |  | 2022-11-18 | 2022-12-09
| 10.4 |  | Team Review | 10.3 | Team will review cad to possibly improve preliminary design | Improved Preliminary Design | team members |  |  | 2022-12-09 | 2023-01-20
| 10.5 |  | Prototype1 | 10.4 | Create prototype for testing | Part for testing | machine shop/materials |  |  | 2023-01-20 | 2023-02-17
| 10.6 |  | Test | 10.5 | Test prototype rigouriously | Knowledge of how well part operated | machine shop/materials |  |  | 2023-02-17 | 2023-03-17
| 10.7 |  | Final Design | 10.6 | Create final cad design for completed product | final design | solidoworks/autocad |  |  | 2023-03-17 | 2023-04-14
| 10.8 |  | Create solidworks design | 4,5,6,7,8,9,10.1-10.7 | Create solidworks design modelling this aspect | solidworks part/assembly | solidworks |  |  | 2023-03-17 | 2023-04-14
| 11 | Contected Functionality
| 11.1 |  | Design Check | 7.3,8.3,9.3,10.3 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-01-16 | 2023-01-19
| 11.2 |  | Prototype1 Check | 7.4,8.4,9.4,10.4 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2023-02-11 | 2023-02-16
| 11.3 |  | Finale Design Check | 7.6,8.6,9.6,10.6 | talk with other groups to make sure designs are compatible | corrections to design | meeting time |  |  | 2022-03-11 | 2022-03-16
12
12.1
12.2
12.3
12.4
12.5
13
13.1
13.2
13.3
13.4
| 14 | Turn in final requirements
| 14.1 |  | Submit Final Report | all of the above | submit final report to canvas | Submitted final report |  |  |  |  | end of semester
| 14.2 |  | Submit Design Package | all of the above | submit final design package to canvas | Submitted final design package |  |  |  |  | end of semester
| 14.3 |  | Present final product | all of the above | present final product to senior expo and sponsor | Completion of product presentation | All team members |  |  |  | end of semester
14.4

## Document changes
Project Plan
Problem Specification
House of Quality