## Sheet1
Weekly Update
| Team: | Evergood
| Week of: | 10/3 - 10/7
Sponsor | Project Lead | # of Team Members |  | Metric |  |  |  |  | G | on Track
Matthew Hexter | Grace Wenham | 5 |  | Baseline |  |  |  |  | A | Off achedule, No milestone Delay expected
Target
Schedule | Issues/Risk | Resources | [6 empty] | R | Off schedule, Milestone Delay Expected
Group meeting on Monday, Thursday in class, and Sunday |  | Hayden took home machine that Matthew gave us (analog wine filler based off of time) to take apart and study and use as reference |  | Action Items/Tasks This Week
|  |  |  | Task # | Action Item | Member | Status |  | C | Complete
Scope |  |  |  | 1.1-1.3 | Submit Initial Project Plan | all | C
Problem Statement |  |  |  | 2.1-2.4 | Submit team contract | all | C
Expected Benefit |  |  |  | 1.5 | Complete weekly Update | Grace | C
|  |  |  | 1.6 | Submit engineering notebook | Grace | C
Upcoming Major Activies |  |  |  | 1.7 | Create schedule for who updates project plan and who submits weekly update every week | Jackson | G | Not yet updated in Project Plan
Milestone | Status | Due Date | Comments
Visit Evergood facility | C | 2022-10-09
Upcoming Activities/Tasks
|  |  |  | Task # | Action Item | Member | Status
|  |  |  | 1.8 | Change weekly faculty meeting time | Brock | G | Not yet entered in Project Plan
|  |  |  | 4 | Email Matthew asking to send us specifications on the canning machine and info about the manufacturer's solution for filling pouches | Hayden | G | Not yet entered in Project Plan
Critical Risks and Issues | Member | Due | Status | 4.1 | Begin market research to gain background information on any mechanisms already available | All | G | Not yet entered in Project Plan