## Sheet1
Weekly Update
| Team: | Evergood
| Week of: | Oct 10-16
Sponsor | Project Lead | # of Team Members |  | Metric |  |  |  | G | on Track
Matthew Hexter | Grace Wenham | 5 |  | Baseline |  |  |  | A | Off achedule, No milestone Delay unexpected
Target
Schedule | Issues/Risk | Resources | [5 empty] | R | Off schedule, Milestone Delay Expected
Action Items/Tasks This Week
|  |  |  | Task # | Action Item | Member | Status | C | Complete
Scope |  |  |  | 2.6 | Create problem statement | Grace | C
Problem Statement |  |  |  | 1.7 | Edit project plan with plan for modelling product online | Grace | C
Expected Benefit |  |  |  | 1.8 | Create schedule for team member completing project plan and weekly update | Jackson | A
|  |  |  | 2.5 | Edit team contract disagreements section | Grace | C
Upcoming Major Activies |  |  |  | 4 | Conduct research about existing automation solutions | All | G
Milestone | Status | Due Date | Comments | 1.5 | Fill out and submit weekly update | Grace | C
Upcoming Activities/Tasks
|  |  |  | Task # | Action Item | Member | Status
|  |  |  | 4 | Conduct research about existing automation solutions | All | G
|  |  |  | 1.8 | Create schedule for team member completing project plan and weekly update | Jackson | G
Critical Risks and Issues | Member | Due | Status | 4.4 | Review manufacturer's solution specifications |  | G