## Sheet1
Weekly Update
| Team: | Evergood Adventure Wines
| Week of: | 10/24-10/31 |  | on Track | G | metric = output of completing this task
Off schedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Spokesperson | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor
|  |  |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
4.1-4.4 | research | all | research at least 2 hours, type findings in teams document(s) | Add research to shared word document | G | On Schedule
4.7 | Complete house of quality | all | submitted to canvas on Friday | Submitted on Canvas | C
4.5 | Complete engineering specification document | all | complete draft and collect signars | All signatures collected | G - final draft complete sending out for signatures
4.6 | share engineering specification document with sponsor | hayden | send document to sponsor | sent document by 11/1/22 | C
4.8 | Meet with sponsor and discuss engineering spec doc | Grace, Ryan | Meet with sponsor | Met with sponsor on Fri 10/29 | C
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
4.1 | Take Apart Pressure Regulator/Pump | all | Pictured and typed findings in teams document. | G | C | Complete research endeavors | G | 2022-11-08
4.1-4.4 | Research | all | typed findings in teams document | G | G
4.9 | Create eng spec outline for report (determine derived reqs, sponsor reqs, ATF reqs) | all | completed outline | G | C