## Sheet1
Weekly Update
| Team: | Evergood Adventure Wine
| Week of: | 11/7/2022-11/14/2022 |  | on Track | G | metric = output of completing this task
Off achedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Spokesperson | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
4.1 | Take Apart Pressure Regulator/Pump | Grace, Hayden, Ryan | Pictured and typed findings in teams document. | typed notes available for team review | C | Right on Track
4.1-4.4 | Research | all | typed findings in teams document | typed notes available for team review | C
4.2 | Research existing solutions - canning machine | Hayden, Jackson | typed findings in teams document | typed notes available for team review | C
4.9 | Create eng spec outline for report (determine derived reqs, sponsor reqs, ATF reqs) | all | completed outline | Outline availble for team review | C
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
4.11 | Complete Specifications Report | all | Completed Specifications Report | G | C | Conduct Research about Subject | G | 2022-11-14
5.1 | Each member brainstorms 1-2 designs with implementations | all | Notes in design notebook and presentable for Team meeting on 11/13 | G | C