## _56F9DC9755BA473782653E2940F9 (hidden)
-kOTUsjon0GrLqcMEAOIEOANcnVmes9GtHhth5J4Eb1UMDc0WDFCMlo3TkpDRVA2TlFBVURGSVRWQSQlQCN0PWcu
Form1
{d3ed2b02-8301-45c3-b347-af8481d50f22}

## Form1
Weekly Update
| Team: | Evergood Wine
| Week of: | Dec 5-10 |  | on Track | G | metric = output of completing this task
Off achedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Member | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
5.8 | Submit team contract for winter break | all | submitted to edusourced | submitted to edusourced | G
5.9 | update project plan | Brock | Project plan completed | submitted project plan | C
4.11 | Finish engineering spec report | Jackson | Spec Report is completed | submitted engineering spec report | G
5.3 | Consolidate and narrow down design ideas | Ryan and Hayden | have notes and ideas to discuss with sponsor | submitted and narrow down design ideas | C
5.5 | Complete Design matrix | Jackson | Decision matrix fully filled out (includes sponsor input) | submitted Design matrix | C
5.8 | Winter Break Team Contract | Grace | Winter break contract signed and submitted to edusourced | submitted Break Team Contract | G
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
5.13 | bring spring semester schedule | all |  | G | G
5.14 | edit and submit eng spec report | all/whoever has time |  | G | G
5.6 | Decide on main idea as a team using decision matrix | all | review output of decision matrix | G | C