## Sheet1
Weekly Update
| Team: | Evergood
| Week of: | 2022-11-14 |  | on Track | G | metric = output of completing this task
Off achedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Member | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor
|  |  |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
4.11 | Complete Specifications Report | all | Completed Specifications Report | G | C | Want to complete brainstorm ideas by Sunday. This is so we can discuss ideas on Sunday.
5.1 | Each member brainstorms 1-2 designs with implementations | all | Notes in design notebook and presentable for Team meeting on 11/13 | G | R | For milestone 4 we still need client to sign off on specification document.
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
5.1 | Each member brainstorms 1-2 designs with implementations | All | Notes in design notebook and presentable for Team meeting on 11/13 | R | C | 4 | G | 2022-11-21 | Still need to complete specification report and have client sign off on specification document
5.2 | Group discussion on Ideas | All | Meet on Nov 20 to discuss all ideas | R | C | 4.6 | G | 2022-11-20
4.6 | Send Eng Spec Doc to sponsor anf faculty to approve and sign | Hayden | Receive signature from sponsor and faculty on eng spec document | R | C | 4.11 | G | 2022-11-21