## Sheet1
Weekly Update
| Team: | Everygood Wine
| Week of: | Nov 20-26 |  | on Track | G | metric = output of completing this task
Off achedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Member | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor
|  |  |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
5.1 | Each member brainstorms 1-2 designs with implementations | All | Notes in design notebook and presentable for Team meeting on 11/13 | C | C | On Track
5.2 | Group discussion on Ideas | All | Meet on Nov 20 to discuss all ideas | C | C
4.6 | Send Eng Spec Doc to sponsor anf faculty to approve and sign | Hayden | Receive signature from sponsor and faculty on eng spec document | G | G
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
5.3 | Consolodate and narrow down design ideas | Ryan and Hayden | have notes and ideas to discuss with sponsor | G | C | 4 | C | 2022-11-21 | Still need to complete specification report and have client sign off on specification document
5.4 | Discuss ideas with sponsor | anyone who can meet at the time | Get feedback from sponsor on ideas before CDR | G | G | 4.6 | G | 2022-11-20
5.5 | Complete Design matrix | Jackson | Decision matrix fully filled out (includes sponsor input) | G | G | 4.11 | G | 2022-11-21
5.6 | CDR report finished | Jackson | CDR Ready to present | G | G
5.7 | CDR presented to sponsor/advisors | All | CDR Signed off and approved | G | G
5.8 | Winter Break Team Contract | Grace |  | G | C
5.9 | update project plan | Brock | Project plan cmpleted | G | G