## Sheet1
Weekly Update
| Team: | Evergood Wine
| Week of: | Nov 28 - Dec 3 |  | on Track | G | metric = output of completing this task
Off achedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Team Member | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
4.11 | Finish engineering spec report | Jackson | Spec Report is completed | Spec report is sent to Mary for edits | C
5.3 | Consolodate and narrow down design ideas | Ryan and Hayden | have notes and ideas to discuss with sponsor | Notes posted in Teams files | C
5.5 | Complete Design matrix | Jackson | Decision matrix fully filled out (includes sponsor input) | Add Weights for Columns | G
5.8 | Winter Break Team Contract | Grace | Winter break contract signed and submitted to edusourced | Posted and signed in Teams | C
5.9 | update project plan | Brock | Project plan completed | Uploaded to Edusourced and Canvas | A
Task # | Action Item | Member | Metric | Status | Target | Upcoming Major Activies
5.5 | Complete Design matrix | All | Decision matrix fully filled out with numbers for each design | G | C | Milestone | Status | Due Date | Comments
5.4 | Discuss ideas with sponsor | anyone who can meet this week | Get feedback from sponsor on ideas before CDR | G | G - Scheduled
5.6 | CDR report finished | All | CDR Ready to present | G | G
5.7 | CDR presented to sponsor/advisors | All | CDR Signed off and approved | G | G