## Sheet1
Weekly Update
| Team: | Evergood
| Week of: | Oct 17-23 |  | on Track | G | metric = output of completing this task
Off schedule, No milestone Delay expected
| Sponsor | Matthew Hexter |  |  | A
| Project Lead | Grace Wenham
| Spokesperson | Hayden Mclaughlin |  | Off schedule, Milestone Delay Expected
| Team Member | Ryan Beckman |  |  | R
| Team Member | Brock Martin
| Team Member | Jackson Taylor
|  |  |  | Complete | C
Action Items/Tasks This Week
Task # | Action Item | Member | Metric | Defined complete | Status | General Comments
4.1-4.4 | Conduct market research | all | listed in Teams | Have material for task 5 | Ongoing | On schedule
| Pouching methods | Grace, Ryan | listed in Teams |  | Ongoing
| FDA reqs | Hayden | listed in Teams |  | Complete
| Water proofing reqs | Hayden | listed in Teams |  | Complete
4.5 | Engineering specification document | Grace, Hayden, Ryan | Have all requirements listed and categorized | List contains all necessary features | Draft completed
2.6 | Edited problem statement, resubmitted team contract with edits | Grace | resubmitted to canvas and edusourced |  | Complete
Upcoming Activities/Tasks | [5 empty] | Upcoming Major Activies
Task # | Action Item | Member | Metric | Status | Target | Milestone | Status | Due Date | Comments
4.1-4.4 | research | all | research at least 2 hours, type findings in teams document(s) | G
4.7 | Complete house of quality | all | submitted to canvas on Friday | G |  | Engineering Specification Document | In Progress | soft deadline: 11/1/2022, hard deadline: dec 2 | Still need to review with client
4.5 | Complete engineering specification document | all | Show faculty at Monday meeting | G |  | Engineering specification Report | Not yet started | soft deadline: 11/10/2022, hard deadline Dec 2 | Show faculty engineering specification document before beginning engineering specification report
4.6 | share engineering specification document with sponsor | hayden | sent document by 11/1/22 | G